## Sheet1
A list of tests and tasks. Some require hardware, some require discussion w/ relevant people
TODO | Started? | Done? | Notes
does readSPI() return values as expected? | Y | N | Hardware Test
does altimeter CHIP_ID reg succeed? | N | N | Hardware Test
does IMU WHO_AM_I reg succeed? | Y | N | Hardware Test
does IMU.readAccelerationZ() return 9.81ms2 at rest? | Y | N | Hardware Test
can IMU acceleration measurement range be set successfully? | Y | N | Hardware Test
does the IMU noise in z-direction match the datasheet for a particular measurement range? | Y | N | Hardware Test
does the noise matrix definition process set properly according to measurements? | Y | N | Software Test
does the iterative matrix calculation process work as compared to manual? | N | N | Software Test
can the micro-SD be found? | N | N | Hardware Test
can the micro-SD be written to? | N | N | Hardware Test
how will startup work? can we wait for a signal from main OBC to begin setup? | N | N | Discussion
replace errFlag with an 8 bit (?) binary code where each bit indicates a different error? | Y | N | All
before going any further, revisit PCB and check all components will fit (RTC seems large!) | N | N | Design
connect CD pin to 7 on PDC with 10k pull-up | N | N | Design
does readI2C() return values as expected? | N | N | Hardware Test
refactor IMU reading (i.e. methods like read.gyro.z()) | Y | N | Design
major main code cleanup (comments, layout, etc.) | Y | N | Design
test the clock signal on pin 9 is at the frequency we want it to be at & constant | N | N | Hardware Test
does doxygen work for arduino & is it worth doing or nah? | N | N | Design